## Sheet1
2010 02 17 |  | Description |  | Action | Date
Location
| x | Version No 3.1 not 12 need to agree | e.g.
| x | News out of date |  | NT
| D | Need to review document type and standardise sub-numbering | Register *R ,List *L ,Claim=64 |  | ASAP
| C | Contract: Sub types still confusing with 1,2,3,4 etc | review w NT | MS
| 0 | Location codes not ideal cannot add in multiple combinations |  | NT
| 0 | Floor levels not in for all stations
| A | Activity to be moved under 2 Technical |  | NT
| 6 | Claims cannot add Claim No |  | NT
| 7 | Audits > Assurance |  | NT
| 7 | Sub division Assurance reqd from MM |  | MM
Help | 8 | Help Text not correct for MET System still using KKK Systsm |  | AH
Help | 9 | Site Documentation | Incorrect see Handbook | AH
| 10 | Statistics does not work
Cannot find under Document Search just adding MET No
Doc List |  | In workflow box current folders has to be changed to all folders | very inconvenient, need above | AH
Doc List |  | Document List ( Search for a Classified Document) does not show docs classified on the first screen. You have to scroll through whole list |  | AH
Doc List |  | Need to be able to search on the original file name within this list | at present need to know original file name | AH