## Sheet1
| Nr. | Prio | Status | Description | Found at | by | Responsible | Termin | Typ | Comment | Comment SoftXS | Status SoftXS
|  | 1: 0 | open: 40
total: 40
General
| 1.1 |  | open | Use light blue background in header of production system to allow to see status information better | 2010-02-03 | MS/MET | SoftXS |  | Configuration
| 1.2 |  | open | Move function “Upload Metadata” from “Document” to “Admin” | 2010-02-03 | MS/MET | SoftXS |  | Configuration
Document File/New
| 2.1 |  | open | Sequence Nr. Not copied from document code to sequence number field | 2010-02-03 | EB/MET | SoftXS |  | Bug
| 2.2 |  | open | Sequence Nr. Must have 6 digits | 2010-02-03 | MS/MET | SoftXS |  | Functionality
| 2.3 |  | open | Hide fields “Document Format', “Layout Type” and “Set classification fields based on document code” | 2010-02-03 | EB/MET | SoftXS |  | Layout
| 2.4 |  | open | Show field “Abstract” on default layout type | 2010-02-03 | EB/MET | SoftXS |  | Layout
| 2.5 |  | open | Hide fields “Planned Scale and Sheet number” | 2010-02-03 | EB/MET | SoftXS |  | Layout
| 2.6 |  | open | Correct type error “Idocument Code” | 2010-02-03 | EB/MET | SoftXS |  | Misstyping
| 2.7 |  | open | Default Work Flow is “NONE” | 2010-02-03 | EB/MET | SoftXS |  | Configuration
| 2.8 |  | open | Set back all “Phase” values from older versions | 2010-02-03 | MS/MET | SoftXS
Document File/Search
| 2.9 |  | open | Rename “Current Contract” to “Current Folder” | 2010-02-03 | EB/MET | SoftXS |  | Terminology
Document List
| 3.1 |  | open | Rename “Contr.” to “Folder” | 2010-02-03 | EB/MET | SoftXS |  | Terminology
| 3.2 |  | open | Align left “Document code” | 2010-02-03 | EB/MET | SoftXS |  | Layout
| 3.3 |  | open | Use only views “Summary”, “Docfile” and “Classification” | 2010-02-03 | EB/MET | SoftXS |  | Layout
Klassification Aspects and values |  |  | open |  | 2010-02-03 |  | SoftXS
| 4.1 |  | open | Rename code “Q093” to “Q309”, etc. | 2010-02-03 | EB/MET | SoftXS |  | Configuration
| 4.2 |  | open | Translate all “xxx” to hungarian | 2010-02-03 | EB/MET | SoftXS |  | Configuration
| 4.3 |  | open | Move Aspect “Activity” under “Technical” | 2010-02-03 | MS/MET | SoftXS |  | Configuration
| 4.4 |  | open | Create new Aspect “Contracts” below “Document type” and move aspect values 17-C there | 2010-02-03 | MS/MET | SoftXS |  | Configuration
| 4.5 |  | open | Rename header of classification block to “Classification/Subject” | 2010-02-03 | MS/MET | SoftXS |  | Terminology
| 4.6 |  | open | Aspect value “06” is not at the correct level | 2010-02-03 | MS/MET | SoftXS |  | Configuration
| 4.7 |  | open | “20” should be “General” and Document type D20.1 Standards D20.2 Specifications | 2010-02-03 | MS/MET | SoftXS |  | Configuration
| 4.8 |  | open | Rename “Audits” to “Quality Assurance” and “70” to “QA General” | 2010-02-03 | MS/MET | SoftXS
| 4.9 |  | open | Define sublevel for “70 – QA General” | 2010-02-03 | MS/MET | SoftXS
| 4.1 |  | open | Create a utility to make a CSV file containing aspect codes and hungarian and english values in different columns | 2010-02-03 | MM/MET | MM/MET |  | Development
Revisions
| 5.1 |  | open | Hide “Scale/Size/Orientation/Revision number” | 2010-02-03 | EB/MET | SoftXS |  | Layout
| 5.2 |  | open | Revision background color is pink if work flow is “NONE”. Should be white. | 2010-02-03 | EB/MET | SoftXS |  | Bug
Documentation/Help
| 6.1 |  | open | Create a Link to Wiki under Site Documentation | 2010-02-03 | EB/MET | SoftXS |  | Functionality
Uploading WebDoc files
| 7.1 |  | open | Doc.code/Phase: Supply construction startdate by contracts to decide phase (3 or 4) | 2010-02-03 | MS/MET | MS/MET |  | Information
| 7.2 |  | open | Doc.Code/Discipline: 3 | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.3 |  | open | Doc.Code/Main aspect: if 9x defined use it, otherwise 91 | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.4 |  | open | Doc.Code Langugae Code: EN | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.5 |  | open | Doc.Code Sequence Number: PDF file number + 100000 or sequential from 190000 if no PDF file defined | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.6 |  | open | Doc. Title1: “DBR Metro 4” | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.7 |  | open | Doc. Title2: English text | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.8 |  | open | Doc. Title3: Edited Hungarian text | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.9 |  | open | Doc. Title4: Original Hungarian text | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.10 |  | open | Revision. Title 2: “DBR Metro 4”+PFD filename | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.11 |  | open | Revision. Title4: Column “CI” to “CN” concatenated with delimiter “*” | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.12 |  | open | Columns “PH No.”, “Ref. No”, “Web Doc Letter No.” concatenated into “External key” | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.13 |  | open | Columns “Letter to” and “Author” into field Author | 2010-02-03 | MS/MET | SoftXS |  | Definition
| 7.14 |  | open | Column “Date” into “Start Date” | 2010-02-03 | MS/MET | SoftXS |  | Definition